The Purpose of the Scope of Work (SOW) Table is to provide a clear and concise description of the services that will be provided with this grant funding. This description needs to contain measurable deliverables so that the Grant Management Unit staff can objectively measure if the program met its goals.

INSTRUCTIONS: Scope of Work (SOW) Table

How to Complete the SOW Table:

- Replace the red text that says “Subrecipient’s Name” with the name of your agency/organization in the sentence under the document name. Please note that this should be the name on your application for funding.

- Replace the red text that says “Subrecipient Name” with the name of your agency/organization in the “Scope of Work for Subrecipient Name” line of the document. Please note that this should be the name on your application.

- Determine how many goals the program funded with this grant will have. You will need to have one Goal Statement and Table with details for each Goal.

  - If your program has only one goal, delete the second goal statement and table from the template form.

  - If your program has more than two goals, copy the goal statement and table and paste it below the second table. Remember to change the numbering. Repeat this until you have the correct number of goals for your program.

- Type the first goal statement for your program above the first table after where it says, “Goal 1:” See below for more details on the differences between a goal, an objective, and an activity.

- Determine the Target Number of the objective you are going to provide to meet your goal. Example below.

- Determine the Objectives that will show how your agency is going to demonstrate that it met its goal and type them in the first column of the table labeled Objectives.

  - Number each objective in the table.

  - Each goal must have at least one objective.

  - Objectives need to be specific and measurable. This means that they most likely will have a number in them.

- Put the target number for each objective in the column labeled “Target Number.”

  - These should be numbered to match the number of the objective that they are connected to.

- Determine the Activities that the agency/organization will need to complete to accomplish the objective.

  - Each Objective must have at least one activity.

  - Number each activity with the number of the objective that it applies to then point and the number of the activity. Example: If the first objective had three activities, they would be numbered 1.1, 1.2., 1.3, then the second objective had two activities, they would be numbered 2.1, and 2.2.

- Determine who is going to provide the activities to achieve the Objective. This job title should be entered into the Responsible Party section.

  - Multiple job titles are okay.

  - These should line up with each objective in the table.

- Determine the documentation needed to measure the objectives and activities to show that they were completed. This documentation may be reviewed by request of the Grant Management Unit.

  - The numbering of the documentation should match the objective that the documentation will support.

Determining the Difference between Goals, Objectives, and Activities

Goal: The object of the agency’s ambition or effort; and aim or desired result. This is a very broad statement on what your agency plans to do with this funding.  It should establish the big picture and include the target population and what benefits/assistance they will receive.

Objective: A concrete, measurable milestone on the way to achieving the goal they relate to.

Activity: Things that happen or are being done to accomplish the objective they relate to.

Documentation: Material that provides official information or evidence or serves as a record of the activities and objectives being completed.

EXAMPLE:

Scope of Work (SOW) Table

Crater Lake Victim Advocacy, hereinafter referred to as Subrecipient, agrees to provide the following services and reports according to the identified timeframes:

Scope of Work for Crater Lake Victim Advocacy

Goal 1: Assist victims in becoming self-sufficient.

| Target Number | Objectives | Activities | Responsible Party | Documentation Needed for Measurement |
| --- | --- | --- | --- | --- |
| 1. 50 2. 50 3. 52 | 1. Provide advocacy 2. Provide education on criminal justice process 3. Provide weekly life skills classes for victims. | 1.1 Operate hotline 1.2 Crisis intervention 1.3 Safety planning 1.4 Basic needs assessment 2.1 VOCA compensation education 2.2 Temporary Protection Order (TPO) education 2.3 Legal resources education and referral 3.1 Parenting classes 3.2 Budgeting/debt management classes 3.3 Employment readiness classes | 1. Advocates 2. Advocate 3. Advocate | 1. Electronic records system 2. Case notes 3. Group sign-in sheets |

Goal 2: Assist victims improve mental health related to victimization.

| Target Number | Objectives | Activities | Responsible Party | Documentation Needed for Measurement |
| --- | --- | --- | --- | --- |
| 1. 10 2. 30 | 1. Provide mental health counseling 2. Provide case management | 1.1 Psychiatric evaluation 1.2 Crisis intervention 1.3 Counseling sessions 2.1 Complete Social history 2.2 Case plans 2.3 Referrals and Follow-up | 1. Counselor 2. Case Manager | 1. Paper counseling charts 2. Electronic records system |

Scope of Work (SOW) Table

Subrecipient’s name, hereinafter referred to as Subrecipient, agrees to provide the following services and reports according to the identified timeframes:

Scope of Work for Subrecipient name

Goal 1: Describe the primary goal the program wishes to accomplish with this subaward.

| Target Number | Objectives | Activities | Responsible Party | Documentation Needed for Measurement |
| --- | --- | --- | --- | --- |
| 1. Total number, not percentage, of victims, training, or classes you hope to achieve in your objective 1. 2. Total number, not percentage, of victims, training, or classes you hope to achieve in your objective 2. | 1. These are specific objectives that need to be made to achieve the Goal. These need to be measurable. 2. | 1.1 These are the activities that can or need to be accomplished to achieve the Objectives 2.1 | 1. 2. | 1. What documentation do you have to show this objective was accomplished? How will you measure the information to show the objective is being met? 2. |

Goal 2: Describe the secondary goal the program wishes to accomplish with this subaward.

| Target Number | Objectives | Activities | Responsible Party | Documentation Needed for Measurement |
| --- | --- | --- | --- | --- |
| 1. 2. | 1. 2. | 1.1 2.1 | 1. 2. | 1. 2. |

Note: This document should not contain any red text when completed.

Note to Preparer: Add lines to the table as applicable to accomplish all the goals of this subaward. Line up activities, Target Number, documentation, and measurements as best as possible for easier analysis.